## Slide 1: Vedik Land
Blog to store all information

## Slide 2: 17JUN 2022
On this day we decided to work with Vishram Bapat Sir .
We will work on a site which will give all the information about INDIAN HISTORY .
We will meet next time to discus more about it on 27Jun2022.

## Slide 3: 27 Jun 2022
We conformed that we want to work on this project .
On this day get to what kind of project is this and this we help people all over the world .
Sir teach us some important lessons to work on this project.
- Feel free to express your problems .
- Be Creative and improve your self.

## Slide 4: 29Jun2022
On this day we decided to meet but we are late and we did not send any message to Sir .
Bapat sir get upset with our behaviour and wants to stop this project with me and shruti .

## Slide 5: 30Jun2022
We get bit confuse because of miscommunication .
We get a conference call and clear it .
We also do a video call to clear it and discuss more about the project .
We will do online meetings while I am in Banglore .
Started preparation to work on this project by leaning new skills .
I was learning photo editing and Shruti digital marketing.
Digital marketing will help as to grow on online platform fast.
Miscommunication is always a bad thing ,always clear it .

## Slide 6: 7Jul2022
Learning new skill is fun.
Discuss some difficulties we were facing .
Try to explore new printing applications like canva …
Learn something about graphics , its tools and got know that we have a graphic designer with as .

## Slide 7: 15Jul20
Get together first time for a online meeting with Bhavna maam .
Got that gamil ID that we wished.
Created a youtube channel.
Started discussing about what to upload on channel.
Discuss about offline meeting in college.

## Slide 8: 2aug2022
Meeting got delay due to my mothers health issues .
Meeting was shift to 2 august 2022 .
This day we officially started our work .
I request principal ma’am to make changes on my time table .
Sir gave as a book related to our topic.
After that we started entering the temples information .

## Slide 9: 7Aug2022
We had online meeting because my timetable was not changed .
Sir was angry on us , because we did not inform sir about my timetable.
We will use group for discussing about projects.